## Progress
Session | Module/Component | Status | Est. Hours | Actual Hours | Tests | Dependencies | Parallel | Start Date | End Date | Notes
00 | Infrastructure Setup | pending | 2 |  | N/A | — | Yes |  |  | Docker, TimescaleDB, Redis
01 | Database Layer | pending | 3 |  | 4 tests | S00 | No |  |  | asyncpg pool, models, migrations
02 | Configuration System | pending | 1 |  | 2 tests | S00 | Yes |  |  | Pydantic settings
03 | WebSocket Client Base | pending | 3 |  | 5 tests | S01, S02 | Yes |  |  | Reconnection logic
04 | Orderbook Collector | pending | 3 |  | 4 tests | S03 | Yes |  |  | Snapshot storage
05 | Trade + Leaderboard | pending | 4 |  | 6 tests | S03 | Yes |  |  | Polling + watchlist
06 | Spike Detection | pending | 3 |  | 5 tests | S04, S05 | Yes |  |  | Z-score algorithm
07 | Wallet Attribution | pending | 4 |  | 5 tests | S06 | Yes |  |  | Leader identification
08 | Community Detector | pending | 5 |  | 4 tests | S05, S07 (+1 week data) | Yes |  |  | HDBSCAN clustering
09 | Scoring Engine | pending | 3 |  | 4 tests | S07 | Yes |  |  | Composite scoring
10 | Signal + Paper Trading | pending | 4 |  | 6 tests | S07, S09 | Yes |  |  | Momentum follow strategy
11 | Risk Manager | pending | 2 |  | 4 tests | S10 | Yes |  |  | Position sizing, circuit breakers
12 | Monitoring & Entry Points | pending | 2 |  | 5 tests | S01-S11 | No |  |  | Prometheus + entry points
13 | E2E Integration Test | pending | 2 |  | 1 test | S12 | No |  |  | Live data validation
Summary
Total Sessions: | 14
Done:
In Progress:
Est. Total Hours:
Actual Total Hours: